## Fit & Proper Tracker
Fit and Compliant Consulting
Fit & Proper Tracker (Team Leader Updates)
Employee Name | Highest Qualification | RE5 Status | CPD Cycle Year | DOFA Date | DOFA Verified | Annual Declaration | Overall Status | Due Date | Evidence Notes

## Milestones & Admin
Milestone / Admin Task | Description | Responsible Party (Student / Employer / Provider) | Due Date | Actual Completion Date | Status (Not Started / In Progress / Completed / Overdue) | Related Student(s) | Evidence Stored (Yes/No) | Evidence Location / Reference | Comments
Induction Session | Kick-off for project/learnership | Provider | 2026-02-21 | 2026-02-21 | Completed | All Students | Yes | Cloud/Induction/
UI Portfolio Submission | First design draft | Student | 2026-03-15 |  | Not Started | STU001, STU003 | No | -
Quarterly Progress Report | Employer feedback report | Employer | 2026-04-01 |  | Not Started | All Students | No | -
Final Exam/Assessment | Final deployment and viva | Provider | 2026-05-15 |  | Not Started | All Students | No | -

## Timelines & Milestones
Fit and Compliant Consulting
Onboarding & Exam Timelines
Milestone Phase | Target Date | Actual Date | Status | Comments
Candidate Onboarding
Study Material Access
Exam Date
Results Received
Follow-up Interview

## Overview
Programme / Learnership Name | Cohort / Group | Employer / Host Company | Start Date | End Date | Coordinator Name | Contact Email | Contact Number | Notes / Special Conditions
Website Redesign Project | Alpha Team 2026 | Internal Digital Dept / Web Agency | 2026-02-20 | 2026-05-21 | Sarah Jenkins | s.jenkins@example.com | +27 11 456 7890 | 3-month intensive redesign sprint
PHASE-LEVEL PROJECT TRACKER (3-MONTH SPRINT)
Phase | Task Description | Owner | Priority | Status | Weekly Milestone / Deadline
Discovery | Stakeholder interviews & Requirements | Sarah J | High | In Progress | Week 1
Discovery | Audit current site & Content gap analysis | Mark K | Medium | Not Started | Week 2
Discovery | User Persona development | Sarah J | Low | Not Started | Week 2
Design | Sitemap and Information Architecture | Emily R | High | Not Started | Week 3
Design | Low-fidelity wireframes (Mobile & Desktop) | Emily R | High | Not Started | Week 4
Design | UI Visual Design & Style Guide | Emily R | Medium | Not Started | Week 5-6
Development | Frontend Framework setup | Dev Team | High | Not Started | Week 7
Development | CMS Integration & Backend | Dev Team | High | Not Started | Week 8-9
Development | Content Migration | Content Team | Medium | Not Started | Week 10
Launch | QA Testing (Functional & Browser) | QA Team | High | Not Started | Week 11
Launch | UAT (User Acceptance Testing) | Stakeholders | High | Not Started | Week 12
Launch | Production Deployment & Go-Live | Dev Ops | Extreme | Not Started | Week 12

## Student Register
Student ID / Employee No. | First Name | Last Name | ID / Passport No. | Employer / Host Company | Line Manager / Team Lead | Programme / Learnership | Start Date | Expected End Date | Status (Active / Completed / Withdrawn / On Hold) | Last Contact Date | Next Planned Contact Date | Contact Type | Support Sessions Completed | Missed Sessions | Escalated Issues (Yes/No) | Escalation Notes | Employer Feedback | Student Feedback | Admin Tasks Outstanding (Yes/No) | Admin Task Notes
STU001 | John | Doe | 940506XXXXXX | ABC Corp | Alice Smith | Web Redesign UI | 2026-02-20 | 2026-05-20 | Active | 2026-02-22 | 2026-02-27 | Site Visit | 4 | 0 | No |  | Good progress | Enjoying the UI phase | No | All docs submitted
STU002 | Jane | Molefe | 961112XXXXXX | XYZ Ltd | Bob Brown | Frontend Dev | 2026-02-20 | 2026-05-20 | Active | 2026-02-22 | 2026-02-27 | Site Visit | 1 | 1 | No |  | Good progress | Enjoying the UI phase | No | All docs submitted
STU003 | Thabo | Dlamini | 930214XXXXXX | ABC Corp | Alice Smith | Web Redesign UI | 2026-02-20 | 2026-05-20 | On Hold | 2026-02-22 | 2026-02-27 | Site Visit | 1 | 1 | No |  | Good progress | Enjoying the UI phase | No | All docs submitted